| Ministry of Transport | OP | D01 |
| --- | --- | --- |
| Managing Authority CF 1164/94/ISPA | RISK MANAGEMENT |
|  | Version : 5 | Date : October 2008 | Page: 1 / 7 |

Purpose

To establish the procedure for holding Risk Management Workshop and ensuring timely follow-up, including Risk Mitigation and Monitoring.

Background

In accordance with rules of sound financial management as well as the risk assessment, mitigation and monitoring framework of the EU funding, each Managing Authority under CF 1164/94 (ex-ISPA IA) should timely apply Risk Management procedures.

Procedure

| # | Action | Function / Person responsible | Timing / Deadline | Standard Form / Template |
| --- | --- | --- | --- | --- |
|  | RISK IDENTIFICATION |
|  | Nominates permanent Risk Assessors | Director of MA CF 1164/94 | At least 3 weeks prior to the (initial) annual risk workshop | Appointment letter |
|  | Initiates Annual Risk Workshop – informing Risk Assessors | Director of MA CF 1164/94 | At least 2 weeks prior to the annual risk workshop | Letter on arranging risk workshop |
|  | Appoint the Chairperson from all Risk Assessors | Director of MA CF 1164/94 | At the work shop | Documented in the Annual Risk Workshop Minutes |
|  | Identifies the risks | Each Risk Assessors individually | At the work shop | List of risks (Annex 1, Step 1 of Risk Database) |
|  | Prepares the consolidated Lists of Risks and distributes it risk assessors for step 2 | Chairperson | At the work shop | Consolidated list of risks (Annex 1 Step 2 of Risk Database) |
|  | ASSESSMENT |
|  | Assesses the impact and probability of each risk from the consolidated list | Each Risk Assessors individually | At the work shop | Risk Assessment Results (Annex 1 Step 2 of Risk Database) |
|  | Prepares consolidated Risk Assessment Results in a graphic or spreadsheet format and initiates a discussion to analyse the results. | Chairperson | At the work shop | Consolidated risk assessment results. Risk database entries (Annex 1 Step 3 of Risk Database –risk assessment results) |
|  | In case of questionable risks, initiates reassessment (Step 2) | Chairperson |  |  |
|  | During the analyses determine the risk tolerance threshold, the measures for the most critical risks, the deadlines and responsible persons (Step 3) | Risk Assessors | At the work shop | (Annex 1 Step 3 of Risk Database – risk assessment results) |
|  | Documents the results of the Annual Risk Workshop in risk database | Chairperson | Within two days of finalisation of Annual Risk Workshop | Risk management database entries and generation of a management plan |
|  | Chair person sending resulting reports for approval to the MA Director | Chairperson | Within two days of finalisation of Risk database entries | Risk management database entries |
|  | RISK MITIGATION |
|  | Appoint persons responsible for mitigating each risk | Director of MA CF 1164/94 | Within 2 weeks after Annual Risk Workshop |  |
|  | Suggest mitigating measures / controls by preparing risk mitigation plan (Annex 3) for the relevant responsibility areas. | Persons responsible | Within 3 weeks after Annual Risk Workshop | Risk mitigation plans (Annex 3) for critical risks. Part 3 of risk database |
|  | Document in the risk database. | Persons responsible |  |  |
|  | Approves risk mitigation plans. Makes suggestions for additions / amendments, if needed. | Head of MA CF 1164/94 | Within 4 weeks after Annual Risk Workshop | Risk mitigation plans (Annex 3) for critical risks. Part 3 of risk database |
|  | Make corrections, document measures / controls according to the management’s decision in risk management database Part 3. | Persons responsible | Within 4 weeks after Annual Risk Workshop On a on-going basis | Risk mitigation plan (Annex 3) |
|  | Send copy of the Risk Mitigation Plan to the Chairperson for updating the Risk database (Part 3 – see Annex 3) | Persons responsible |  |  |
|  | Obtain the finalised risk mitigation plans; updating Risk Database (Part 3 – see Annex 3) | Chairperson | Within four weeks after Annual Risk Workshop | Part 3 of risk database (Annex 3) |
|  | MONITORING |
|  | Submit the updated risk mitigation plans prior to quarterly MA meetings to the Chairperson for updating the risk database (part 3 ) | Responsible persons | Quarterly input and review | Risk mitigation plan (Annex 3) |
|  | Obtain the updated risk mitigation plans and update Risk Database (Part 3 – see Annex 3) | Chairperson | On a on-going basis | Part 3 of risk database (Annex 3) |
|  | Initiate quarterly MA meetings for monitoring the achievement of the objectives set in the Risk Mitigation Plans. | Chairperson | Quarterly | Letter on arranging meetings |
|  | Organise quarterly MA meetings and issuing the minutes of meetings to the participants. | Chairperson | 1 week after quarterly MA meeting | Minutes of quarterly MA meetings |
|  | Prepares Updated Risk mitigation plans to be reported on the quarterly meetings. | Chairperson | By quarterly meeting | Updated risk mitigation plans (updated part 3 of risk database) – Annex 2 |
|  | Prepares updated Risk Management Plan to be reported on the annual administration system risk meeting with all MAs and PA. | Chairperson | 1 week before the annual risk meeting | Updated Risk Management plan at the end of the year (updated part 2 of risk database) – Annex 2 |

Annex 1	List of Risks and risk assessment results (Part 1 of the Risk Database)

### Step 1	List of Risks

| No | Objective | Risk |
| --- | --- | --- |
| 1 | 2 | 3 |

### Step 2 	Individual Risk assessment

| Ref. | Objective | Risk | Impact | Probability |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |

### Step 3 	Analysis and Interpretation of the Risk Assessment Results

| Ref. | Objective | Risk | Aggregate Impact | Aggregate Probability | Aggregate risk score (ARS) |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |

Annex 2	Risk Management Plan (Part 2 of the Risk Database)

| Item Number | Risks in priority order | ARS | Preferred treatment options | Estimated ARS after treatment | Efficiency consideration A: accept B: reject | Responsible person | Deadline for implementation | How the risk and its treatment will be monitored |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

|  | Name | Signature and date |
| --- | --- | --- |
| Prepared by |  |  |
| Checked by |  |  |
| Approved by |  |  |

Annex 3	Risk Mitigation Plan for Critical Risks (Part 3 of Risk Database)

| No of risk | Category | Group | Type of risk | Risk position | Risk position after the treatment | Deadline for risk solution |
| --- | --- | --- | --- | --- | --- | --- |
|  | e.g. Financial management | e.g. Payments administration | e.g. Efficiency | [rank in the ARS list] | [rank in the ARS list) | e.g. Continuous |
| Recommended solutions |  |
| Planned actions |  |
| Resources requirements |  |
| Responsibilities for risk management |  |
| The way of monitoring and required reports |  |

|  | Name | Signature and date |
| --- | --- | --- |
| Prepared by |  |  |
| Checked by |  |  |
| Approved by |  |  |

RISK MITIGATION MONITORING

| First Quarterly Monitoring Meeting | Date: |
| --- | --- |
| Up-dated status of mitigation measures |  |
| Actions by the next monitoring meeting |  |

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by |  |  |  |
| Approved by |  |  |  |

RISK MITIGATION MONITORING

| Second Quarterly Monitoring Meeting | Date: |
| --- | --- |
| Up-dated status of mitigation measures |  |
| Actions by the next monitoring meeting |  |

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by |  |  |  |
| Approved by |  |  |  |

RISK MITIGATION MONITORING

| Third Quarterly Monitoring Meeting | Date: |
| --- | --- |
| Up-dated status of mitigation measures |  |
| Actions by the next monitoring meeting |  |

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by |  |  |  |
| Approved by |  |  |  |

RISK MITIGATION MONITORING

| Fourth Quarterly Monitoring | Date: |
| --- | --- |
| Up-dated status of mitigation measures |  |
| Actions by the next monitoring meeting |  |
| Recommendations given to the Annual Risk Assessment Workshop |  |

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared by |  |  |  |
| Approved by |  |  |  |

# Footnotes

The table is the outcome of Risk Identification.

The table is the outcome of Risk Assessment.

Before this template is given to the individual Risk Assessors, the list of risks shall be complete (e.g. Step 1 should be completed)

The Chairman shall copy the objectives and the full list of risks into this table.  Columns 4 and 5 shall be empty when the table is sent to each Risk Assessor for individual assessment. Risk Assessors shall fill in columns 4 and 5 and send the table back to the Chairman, who shall thereafter perform the Risk Analysis.

The table is the outcome of Risk analysis.

Before this template is given to the individual Risk Assessors, the list of risks shall be complete (e.g. Step 1 should be completed)

Column No 4 is the arithmetical average of all assessors’ assessments on the impact risk could have once realised (e.g. once all assessors have assessed all risks, the arithmetical average per each risk is calculated; the arithmetical average is found separately for impact and for probability).

In the column No 5 is the arithmetical average of all assessors’ assessments on the probability of risk realisation.

In the column No 6 is the aggregate risk score (ARS) which is the multiplication of columns 4 and 5 - the aggregate impact and probability per each risk . The table is sorted by ARS in descending order (For purposes of the Risk database file)

ARS – Aggregater Risk Score